## Sheet1
HMGP ACQUISITION AND DEMOLITION CHECKLIST
Note - open space compliance MUST be achieved within 90 days of acquisition for each property. If acquired properties are not compliant with open space regulations in this timeframe, costs for the acquisition and demolition of that property may not be eligible to the grant. Extensions to the timeframe will only be considered for extraordinary circumstances which have occurred (these circumstances may not be anticipated). This checklist encompasses all items from the 19 point checklist for demolition.
Property Address:___________________________________________________________________________________________________
Grants Involved: Acquisition (HMGP) project #__________ Demolition (PA PW # or HMGP project #)__________ Other__________
Pre-Acquisition / Pre-Demolition Requirements
Item | Action | Initials | Date | Notes
1 | Establish a property management file for each parcel to be acquired. One (1) copy each for Local and State records management. |  |  | Take pre-demolition photos with GPS coordinates (See item 19).
2a (HMGP) | Complete NEPA Environmental Review for HMGP Commercial - FEMA |  |  | Properties which are or were commercial in nature, or are adjacent to such, must have a completed environmental site assessment, reviewed and accepted by HSEMD and FEMA, prior to acquisition.
2b | Complete Historic Preservation-Archaeological Review (including draft form of Memorandum of Agreement as necessary) |  |  | Any provision in MOA which would require demolition to occur more than 90 days after acquisition may not be supported by HSEMD / FEMA.
3 | Complete DNR Environmental Review |  |  | Template letter and instructions available through HSEMD. This step should be completed for all properties as soon as the final property list is established, no later than 30 days prior to acquisition.
4 (HMGP) | Complete Duplication of Benefits check (obtain official DOB settlement sheet) |  |  | If the property has NFIP flood insurance, Item #7 will be required.
5 (HMGP) | Develop a schedule for the Acquisition and Demolition of all properties (one per project), submit for HSEMD review and approval |  |  | Once acquired, property must be converted to open space within 90 days. A detailed schedule will be necessary. Schedule must identify the number of necessary contracts and dates that RFPs for demolition services will be posted, dates contractors will be selected, date work will begin for each property (asbestos survey, abatement, structural demolition) and date work will be complete. Acquisition dates must not be more than 90 days prior to the date of open space compliancy.
6 | Draft Request(s) for Proposals and/or Contract(s) for use in procurement of all demolition services / all properties, submit for HSEMD review and approval |  |  | RFP(s) and Contract(s) for Asbestos Abatement may be combined with that for Structural Demolition for expedited procurement of these services, as well as expedited completion of work. HSEMD must review all procurement documentation prior to execution.
7 | Submit "Assignment of Coverage D" form for properties with NFIP / ICC Coverage |  |  | If the property is substantially damaged and has NFIP flood insurance (see Item #4), assign Increased Cost of Compliance (ICC) coverage claim for structural removal costs to the Community.
8 | Verify Personal Property Removal |  |  | Costs to remove personal property are not allowable. Photograph the site after this item is complete or day of acquisition.
9 (HMGP) | Request Notice to Proceed with Acquisition and Demolition (Mitigation Project Officer will issue) |  |  | Notice to proceed must consider proposed acquisition dates where the subsequent 90 day demolition timeframe will intersect winter months of December - February. This is due to the certainty of freezing temperatures which result in a delay to open space compliance (asbestos abatement / utility disconnection).
10 | Conduct Building Inspection as needed |  |  | Determines if structure is safe to enter. If safe, proceed to item 11 & 12. If unsafe, RACM demolition.
11 | Conduct Public Health Inspection, as needed
12 | Conduct Fire Inspection, as needed
I, the undersigned Authorized Applicant Official, hereby certify that the above items have been completed and the corresponding documentation is contained in the property management file. Proof of property settlement (HUD 1 Settlement Statement) has been provided to (HSEMD Project Officer name)________________________________________________. _________________________________________________ ______________________________________________________________________ Printed Name and Title Signature
Settlement Date |  | Open Space Compliance Due Date
Demolition Requirements
Item | Action | Initials | Date | Notes
13 | Provide Public Notification of Demolition |  |  | Publish notice of demolition; placard the structure
14 | Verify Structure is Unoccupied
15 | Cap Well, Water, Sewer and Septic Lines; Disconnect Gas & Electric Service; Remove Popane Tanks
16 | Mark Easements and Underground Utilities
17 | Identify / Remove / Dispose of Asbestos, Lead Based Paints and Other Hazardous Materials per State Environmental and EPA Requirements
18 | Ientify / Remove / Dispose of all HHW per State Environmental and EPA Requirements
19 | Document that Property is Open Space Compliant. Photograph Site Before and After Demolition with GPS Coordinates and Address
All completed documentation is compiled within the Property Management File for each individual structure / property. I, the undersigned Authorized Applicant Official, hereby certify that the property is compliant with 44 CFR part 80.17(d), and that all processes and documentation contained in this checklist are complete. _________________________________________________ ______________________________________________________________________ Printed Name and Title Signature
20 | All Contracted Demolition Services are Complete |  |  | Removal of improvements and debris, site restoration & stabilization, storage & septic tanks, basement, utility and well termination complete.